## Sheet1
STAGE -1 | PLANNING |  |  | 09/28/15 - 10/12/15
Requirement Gathering
Planning for Architecture
Deciding Front End Tools
Deciding Back End Tools
Identification of GPS coordinates
Documentation: (a) NFR (b) FR
Final High Level Architecture
Development of PRD
Test on Alize
Decide test strategies
Create UserStory Board
STAGE-2 | DEVELOPMENT (FrontEnd)+Logics |  |  | 10/13/2015- 11/15/15
IOS/ANDROID
Professor Part |  |  | Student Part
Splash Screen |  |  | Splash Screen
Login/Register |  |  | Login/Register
Registration Form |  |  | Registration Form
Prof Dashboard |  |  | Record Voice Sample
Open Menu |  |  | Student Dashboard
Manage Course |  |  | Open Menu
View Class Detail |  |  | Manage Course
Manual Attendance (A) (B) |  |  | View Class Detail
All Toasts |  |  | Check In
All Toasts
| Development (BackEnd)+Logics | (BackEnd) + Logics
RestEndpoint (UI) |  |  | Rest Endpoint
Basic Prototype of Alize |  |  | ALIZE Set up
Creating UML's |  |  | Database
Unit Test |  |  | ALIZE Integration
Testing/QA
Generate Test cases on PRD
Navigation Testing for UI Screens
STAGE-3 | INTEGRATION & CHECK |  |  | 11/16/15 - 12/18/15
FRONT END
API integration
Unit Test
BACKEND
Alize- Rest Integration
Testing/QA
Regression testing with logics BE+FE screens
Generate necessary test cases (if required)
Integration/System Testing
Documentation
NFR/FR
UML's
Test cases
PRD
STAGE- 4 | Buffer Period+Mock Presentation |  |  | 12/18/15 - 01/03/16
Discussion
Dashboard data API?
Attended 4 out of 5 times. Where does this 5 come from?
Remove list for Report/Attendance? (abort if it will add too much work for Testers?)
Voice file name format
Test results for updated and integratd screens
Final Booth Presentation |  |  |  | 2016-01-04